## Sheet1
System Name: Community Bartering
Members: | [12 empty] | A. MATH LEE ASSIGNED FEATURES: | B. KEITH ASSIGNED FEATURES: | C, MARYLLE ASSIGNED FEATURES:
A. Math Lee Biacolo | [12 empty] | * User Registration and Profiles | * Item Listing | * Exchange Proposal System & Offer Management
B. Keith Tagarao | [12 empty] | * Search and Browse | * Rating and Review | * Notification
C. Marylle Lomeda
[13 empty] | User Registration and Profiles | ITEM LISTING ROADMAP: | FEATURES ROADMAP:
Statuses |  | Todo | [10 empty] | Frontend (UI) | Landing Page UI/UX
|  | In-Progress | [10 empty] | User Registration UI
|  | Done | [10 empty] | User Profile UI | Item Listing Display UI/UX
|  | On-hold | [10 empty] | User Login UI
[5 empty] | September |  |  |  | October |  |  |  | Home UI | Item Listing Create UI/UX
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Home (Login & Registration) UI
[13 empty] | Backend | Item Read/Update/Delete Algorithm
User Registration UI | A | 2024-09-15 | 2024-09-23 | [9 empty] | User Registration Code
User Profile UI | A | 2024-09-15 | 2024-09-23 | [9 empty] | User Login Code
Profile Management Code
Item Listing Landing Page UI/UX | B | 2024-09-22 | 2024-09-24 | [10 empty] | RATING AND REVIEW ROADMAP:
Transaction Rating UI/UX
User Review UI (connected with URP)